## Summary Log
PSP0 Summary Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Justin Sanders
ID: | 00973903
Times Summary
Total time spent on each phase (in minutes)
|  | Planned | Actual | %
| Analysis | 15 | 19 | 7.037%
| Design | 15 | 75 | 27.78%
| Implementation | 45 | 162 | 60%
| Testing | 10 | 14 | 5.185%
| TOTAL | 85 | 270 | 100%
Errors Summary
Errors found on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 1 | 20%
| Implementation | 4 | 80%
| Testing | 0 | 0%
| TOTAL | 5 | 100%
Errors fixed on each phase (in number)
|  | Actual | %
| Analysis | 0 | 0%
| Design | 0 | 0%
| Implementation | 5 | 100%
| Testing | 0 | 0%
| TOTAL | 5 | 100%

## Time Log
PSP0 Time Log
CPSC 280: Introduction to Software Engineering
Assignment #1
Name: | Justin Sanders
ID: | 00973903
Time Entries
EXAMPLE
0 | Design | 2018-11-05 08:15 | 2018-11-05 09:29 | 2 | 72 | Identified data structures needed (map & list). Mom texted.
Interruptions
| Phase | Start Date/Time | End Date/Time | (in minutes) | Actual | Comments
1 | Analysis | 2022-01-18 15:44 | 2022-01-18 16:03 |  | 19 | Read directions, watched quick gradle tutorial video
2 | Design | 2022-01-18 16:15 | 2022-01-18 16:35 |  | 20 | Thinking about how to determine chesspiece locations
3 | Implementation | 2022-01-18 14:45 | 2022-01-18 15:30 |  | 45 | Forgot to note that I set up initial commit and cradle project. Fixed SSH key, New local repository. Added cradle.build, Chesstest.java, Created placeholder Chess class
4 | Design | 2022-01-18 18:11 | 2022-01-18 18:35 |  | 24 | Deciding how to access each piece using 2 for loops and deciding (row,col) potentially
5 | Design | 2022-01-18 18:44 | 2022-01-18 18:53 |  | 9 | Determine each king location and move from there to find other pieces ie.. White king is (0,4) now look for things that could take it
6 | Design | 2022-01-19 14:50 | 2022-01-19 15:12 |  | 22 | Wrote sudo code for piece functions
7 | Implementation | 2022-01-19 15:13 | 2022-01-19 15:53 | 10 | 30 | Interrupted by mother (She is in a bad mood today). Implementing the pawn function.
8 | Design | 2022-01-19 15:53 | 2022-01-19 15:53 |  | 0 | Realized my current setup for comparing king to each individual pawn was gonna be time consuming. Deciding to find king and then search around it for the other pieces instead.
9 | Implementation | 2022-01-19 15:53 | 2022-01-19 16:37 |  | 44 | Added in pawn and knight function
10 | Implementation | 2022-01-20 14:32 | 2022-01-20 15:15 |  | 43 | Finished remaining functions and fixed errors during this time. This project took me way longer than I expected (Partially due to System issues though)
11 | Testing | 2022-01-20 15:15 | 2022-01-20 15:29 |  | 14 | Had been testing throughout the process but ran final ChessTest.java and got 16/16
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
26 |  |  |  |  | 0
27 |  |  |  |  | 0
28 |  |  |  |  | 0
29 |  |  |  |  | 0
30 |  |  |  |  | 0
31 |  |  |  |  | 0
32 |  |  |  |  | 0
33 |  |  |  |  | 0
34 |  |  |  |  | 0
35 |  |  |  |  | 0
36 |  |  |  |  | 0
37 |  |  |  |  | 0
38 |  |  |  |  | 0
39 |  |  |  |  | 0
40 |  |  |  |  | 0
41 |  |  |  |  | 0
42 |  |  |  |  | 0
43 |  |  |  |  | 0
44 |  |  |  |  | 0
45 |  |  |  |  | 0
46 |  |  |  |  | 0
47 |  |  |  |  | 0
48 |  |  |  |  | 0
49 |  |  |  |  | 0
50 |  |  |  |  | 0

## Errors Log
PSP0 Errors Log
CPSC 280: Introduction to Software Engineering |  |  |  |  | Error Types
Assignment #1 |  |  |  |  | Compile | Compile error takes 30+ seconds to fix
[5 empty] | Logic | Misinterpreting or incorrectly implementing (Requirements¦Specification¦Design¦Code)
Name: | Justin Sanders |  |  |  | System | Device (Computer¦Network) or Environment (OS¦JDK¦Eclipse¦git) is missing, misconfigured, used improperly or malfunctioning
ID: | 00973903
Error Entries
EXAMPLE
0 | 2018-11-05 22:42 | Compile | Design | Implementation | 15 | Wrote Comparator objects to sort using different criteria (Comparable only allows for 1 criteria).
Time to Fix
| Happening Time | Type | Inserted | Removed | (in minutes) | Description
1 | 2022-01-18 14:45 | System | Implementation | Implementation | 20 | Did not save SSH key when I made it in the first class. Had to re-do ssh key setup.
2 | 2022-01-18 18:11 | System | Design | Implementation | 5 | My project randomly disappeared and wasn’t saved in my workspace. Copied it back from local repo.
3 | 2022-01-19 16:37 | System | Implementation | Implementation | 15 | Tried to commit andthen all my files disappered again. This is anoying. Just re making gradle project from scratch.
4 | 2022-01-20 15:00 | Logic | Implementation | Implementation | 5 | Pawns directions were incorrect per team. Y axis on my board is reversed, positive y means down. X remains the same though
5 | 2022-01-20 15:00 | Compile | Implementation | Implementation | 10 | Bishop and rook functions were sending invalid index error. This was because of certain syntaxx that I used for the while loops
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50